Wintel Server Build Project Steps

| Name | Estimated Work Effort Hours for 1 Server | Work Effort hours for 500 servers | Duration for 500 Servers |
| --- | --- | --- | --- |
| Server Management - Distributed Unix, Intel, Linux |  |  |  |
| Server Configuration |  |  |  |
| Verify Due Diligence data | 0.4 | 24 | 3 days |
| Develop change plans/create changes to update server firmware/microcode - Group 1 | 0.16 | 80 | 10 days |
| Develop change plans/create changes to update server firmware/microcode - Group 2 | 0.16 | 80 | 10 days |
| Develop change plans/create changes to update server firmware/microcode - Group 3 | 0.16 | 80 | 10 days |
| Develop change plans/create changes to update server firmware/microcode - Group 4 | 0.01 | 5 | 1 day |
| Install firmware/microcode patches to update servers - Group 1 | 0.08 | 40 | 5 days |
| Install firmware/microcode patches to update servers - Group 2 | 0.16 | 80 | 10 days |
| Install firmware/microcode patches to update servers - Group 3 | 0.16 | 80 | 10 days |
| Install firmware/microbe patches to update servers - Group 4 | 0.016 | 8 | 2 days |
| Develop change plans and create changes to patch server OS - Group 1 | 0.16 | 80 | 10 days |
| Develop change plans and create changes to patch server OS Group 2 | 0.16 | 80 | 10 days |
| Develop change plans and create changes to patch server OS - Group 3 | 0.16 | 80 | 10 days |
| Develop change plans and create changes to patch server OS - Group 4 | 0.02 | 10 | 2 days |
| Install Maintenance Levels and patches to update servers Group 1 | 0.16 | 80 | 10 days |
| Install Maintenance Levels and patches to update servers - Group 2 | 0.16 | 80 | 10 days |
| Install Maintenance Levels and patches to update servers - Group 3 | 0.16 | 80 | 10 days |
| Install Maintenance Levels and patches to update servers - Group 4 | 0.02 | 10 | 2 days |
| Install/update other SA tools on servers(e.g., SSH/VNC - Group 1 | 0.05 | 25 | 4 days |
| Install/update other SA tools on servers(e.g., SSH/VNC Group 2 | 0.05 | 25 | 4 days |
| Install/update other SA tools on servers(e.g., SSH/VNC Group 3 | 0.05 | 25 | 4 days |
| Install/update other SA tools on servers(e.g., SSH/VNC Group 4 | 0.05 | 25 | 4 days |
| Tools Infrastructure Deployment |  |  |  |
| Create Server Images | 0.12 | 60 | 12 days |
| HW/SW Acquired | 0.088 | 44 | 24 days |
| Configs Submitted | 0.008 | 4 | 0.5 days |
| Quotes Obtained | 0.008 | 4 | 0.5 days |
| Request and receive Capital approval | 0.016 | 8 | 2 days |
| Order Equipment | 0.016 | 8 | 1 day |
| HW/SW Order processed | 0.04 | 20 | 20 days |
| Network Connectivity | 0.008 | 4 | 2 days |
| Request Network drops | 0.008 | 4 | 2 days |
| Server Builds |  |  |  |
| Power and floor space requested. | 0.001 | 0.5 | 0.25 days |
| Floor/Rack Space Acquired | 0.001 | 0.5 | 1 day |
| Machines Installed into Racks or floor position | 0.08 | 40 | 2.5 days |
| Infrastructure Machines attached to network, Racked & Stacked | 0.016 | 8 | 5 days |
| UNIX Build Equipment & OS Installations AIX Servers | 0.32 | 160 | 5 days |
| GCMS Servers (TADDM) - Prod & Test | 0.08 | 40 | 5 days |
| Tivoli Servers - TEC, TMR, DB | 0.08 | 40 | 5 days |
| Network Install Management (NIM) - Prod & Test | 0.08 | 40 | 5 days |
| Parity - Prod & Test | 0.08 | 40 | 5 days |
| INTEL Build Equipment & OS Installation INTEL Servers | 0.4 | 200 | 5 days |

| Name | Estimated Work Effort Hours for 1 Server | Work Effort hours for 500 servers | Duration for 500 Servers |
| --- | --- | --- | --- |
| TSM - Prod & Test | 0.08 | 40 | 5 days |
| Citrix - Prod & Test | 0.08 | 40 | 5 days |
| Smarts Appl/DB - Prod & Test | 0.08 | 40 | 5 days |
| Smarts GPR - Prod & Test | 0.08 | 40 | 5 days |
| Tivoli Gateways - Prod & Test | 0.08 | 40 | 5 days |
| Update the maintenance agreement with new location. | 0.02 | 10 | 3 days |
| Notify Delivery Towers - Server Build completed | 0.002 | 1 | 0.25 days |
| Server Management |  |  |  |
| Web Servers | 0.024 | 12 | 5 days |
| Develop change plans and create changes to patch server web software | 0.016 | 8 | 4 days |
| Install Web software patches to update servers | 0.008 | 4 | 1 day |
| email and Collaboration Services Servers | 0.024 | 12 | 5 days |
| Develop change plans and create changes to patch email and Collaboration Services | 0.016 | 8 | 4 days |
| Install email and Collaboration Services patches to update servers | 0.008 | 4 | 1 day |
| Application Servers (if applicable) | 0.024 | 12 | 5 days |
| Develop change plans and create changes to patch Applications | 0.016 | 8 | 4 days |
| Install Application patches to update servers | 0.008 | 4 | 1 day |
| Database Servers (if applicable) | 0.024 | 12 | 5 days |
| Develop change plans and create changes to update Database server configurations | 0.016 | 8 | 4 days |
| Execute changes to Database server configurations | 0.008 | 4 | 1 day |
| HA Servers (if applicable) |  |  |  |
| Develop change plans and create changes to test server failover | 0.004 | 2 | 4 days |
| Execute server failover tests | 0.024 | 12 | 3 days |
| Analyze and document failover test results | 0.016 | 8 | 2 days |
| Develop change plans and create changes to correct server failover problems | 0.008 | 4 | 1 day |
| Execute server failover changes and retest | 0.032 | 16 | 2 days |
| Citrix |  |  |  |
| Generate Application & Firewall Port Requirements | 0.12 | 60 | 5 days |
| Validate & Resolve Internet Connectivity for OS and Citrix Patches | 0.032 | 16 | 2 days |
| Citrix Admin & AD Technical Access to Customer | 0.272 | 136 | 12 days |
| Submit Citrix & AD Team Member - Citrix and Server Access Credentials | 0.24 | 120 | 10 days |
| Citrix Admins Access Tested & Complete | 0.032 | 16 | 2 days |
| M S P Competencies User-Group-Application Citrix Scope | 0.184 | 92 | 11.5 days |
| Generate Group, Application, and User Templates | 0.048 | 24 | 3 days |
| Distribute Templates to Tower TMs | 0.048 | 24 | 3 days |
| Identify M S P Service Support Groups | 0.08 | 40 | 5 days |
| Submit AD Group Requests to customer for Citrix Groups | 0.008 | 4 | 0.5 days |
| Server OS & Build Routine | 0.024 | 12 | 7 days |
| Install OS and Standard Toolsets | 0.002 | 1 | 1 day |
| Download and Install OS Patches and Drivers | 0.002 | 1 | 1 day |
| Generate AD & Citrix Team User IDs | 0.02 | 10 | 5 days |
| Citrix Layer Configuration | 0.192 | 96 | 10 days |
| Identify Active Directory Forests | 0.032 | 16 | 2 days |
| Test Connectivity to AD Forests and Domains | 0.064 | 32 | 2 days |

| Name | Estimated Work Effort Hours for 1 Server | Work Effort hours for 500 servers | Duration for 500 Servers |
| --- | --- | --- | --- |
| Install Citrix Server Layer | 0.08 | 40 | 5 days |
| Configure Citrix Application Layer | 0.016 | 8 | 1 day |
| M S P Support Farm - Application Installation & Publishing | 0 |  |  |
| M S P Support Farm - Application Publishing | 0 |  |  |
| AD Users & Computers - Forest 1 | 0 |  |  |
| Collect Domain Names & Paths | 0.016 | 8 | 1 day |
| Forest Trust - Identify Port Requirements | 0.008 | 4 | 0.5 days |
| Publish Domain/Path | 0.08 | 40 | 5 days |
| AD Transitive Trust Enabled | 0.016 | 8 | 1 day |
| AD Access to Domain Functionality Tested Successfully | 0.008 | 4 | 0.5 days |
| Active Directory Tool | 0.104 | 52 | 6.5 days |
| AD Tool - Collect Install Docs, Requirements, Path | 0.016 | 8 | 1 day |
| AD Tool - Identify Port Requirements | 0.008 | 4 | 0.5 days |
| AD Tool - Publish Link on M S P Citrix Farm | 0.08 | 40 | 5 days |
| Filezilla Client | 0 |  |  |
| Filezilla - Collect Application Codes, License, Install Docs | 0.008 | 4 | 0.5 days |
| Filezilla - Application Port Requirements Identified | 0.008 | 4 | 0.5 days |
| Filezilla - Application Installed | 0.08 | 40 | 5 days |
| Filezilla - Application Functionality Test | 0.008 | 4 | 0.5 days |
| Internet Explorer Client | 0 |  |  |
| IE - Collect Application Codes, License, Install Docs | 0.008 | 4 | 0.5 days |
| IE - Application Port Requirements Identified | 0.008 | 4 | 0.5 days |
| IE - Application Installed | 0.08 | 40 | 5 days |
| IE - Application Functionality Test | 0.008 | 4 | 0.5 days |
| Putty (Secure Telnet) Client | 0 |  |  |
| Putty - Collect Application Codes, License, Install Docs | 0.016 | 8 | 1 day |
| Putty - Application Port Requirements Identified | 0.016 | 8 | 1 day |
| Putty - Application Installed | 0.016 | 8 | 1 day |
| Putty - Application Functionality Test | 0.016 | 8 | 1 day |
| RDP Client | 0 |  |  |
| RDP - Collect Application Codes, License, Install Docs | 0.016 | 8 | 1 day |
| RDP - Application Port Requirements Identified | 0.016 | 8 | 1 day |
| RDP - Application Installed | 0.016 | 8 | 1 day |
| RDP - Application Functionality Test | 0.016 | 8 | 1 day |
| M S P User Credentials | 0 |  |  |
| Steady-State Resources | 0 | 0 | 0 days |
| M S P US Support User & Group Access Testing | 0.112 | 56 | 6 days |
| User Group 1 - Citrix User menus created | 0.016 | 8 | 1 day |
| Generate Citrix Access & Menu Instruction Set for M S P IT Users | 0.016 | 8 | 1 day |
| User Group 1 - Identify Application & Credential Test Participants | 0.008 | 4 | 1 day |
| User Group 1 - Test Bridge Scheduled | 0.008 | 4 | 1 day |
| User Group 1 - Citrix Groups Tested & Complete | 0.032 | 16 | 1 day |
| User Group 1 - ID Credentials Tested & Complete | 0.032 | 16 | 1 day |
| Console Operations - Distributed | 0 |  |  |
| Deployment/Production Phase - Distributed | 0 |  |  |
| Tool Infrastructure | 0.064 | 32 | 4 days |
| Monitoring / Recover Tools | 0.116 | 58 | 10 days |
| Netview/NMC | 0.116 | 58 | 10 days |
| Determine if Shared or Dedicated Infrastructure will be used | 0.02 | 10 | 10 days |
| Obtain User IDs | 0.016 | 8 | 6 days |
| Verify User ID's | 0.08 | 40 | 10 days |
| Configuration Tool | 0.064 | 32 | 4 days |

| Name | Estimated Work Effort Hours for 1 Server | Work Effort hours for 500 servers | Duration for 500 Servers |
| --- | --- | --- | --- |
| Scheduling / Batch Tool | 0.048 | 24 | 3 days |
| Knowledge Transfer | 0.032 | 16 | 4 days |
| DBA Transformation | 0 |  |  |
| DB2 | 0 |  |  |
| M S P DB2 CONNECTIVITY/ACCESS | 0.012 | 6 | 1 day |
| DBA TECHNICAL ASSESSMENT / GAP ANALYSIS | 0.046 | 23 | 5 days |
| DBA SECURITY / PROCESS REVIEW | 0.09 | 45 | 10 days |
| DBA SUPPORT CUSTOMIZATION | 0.102 | 51 | 10 days |
| Oracle | 0 |  |  |
| M S P Oracle CONNECTIVITY/ACCESS | 0.006 | 3 | 1 day |
| Oracle TECHNICAL ASSESSMENT / GAP ANALYSIS | 0.014 | 7 | 5 days |
| Oracle SECURITY / PROCESS REVIEW | 0.028 | 14 | 10 days |
| Oracle SUPPORT CUSTOMIZATION | 0.048 | 24 | 10 days |
| SQL | 0 |  |  |
| M S P SQL CONNECTIVITY/ACCESS | 0.004 | 2 | 1 day |
| DQL TECHNICAL ASSESSMENT / GAP ANALYSIS | 0.006 | 3 | 5 days |
| SQL SECURITY / PROCESS REVIEW | 0.092 | 46 | 10 days |
| SQL SUPPORT CUSTOMIZATION | 0.044 | 22 | 10 days |
| Sybase | 0 |  |  |
| M S P Sybase CONNECTIVITY/ACCESS | 0.002 | 1 | 1 day |
| Sybase TECHNICAL ASSESSMENT / GAP ANALYSIS | 0.012 | 6 | 5 days |
| Sybase SECURITY / PROCESS REVIEW | 0.022 | 11 | 10 days |
| Sybase SUPPORT CUSTOMIZATION | 0.014 | 7 | 10 days |
| DBA NEW ENVIRONMENT BUILD | 0 |  |  |
| Gather Detailed New Build Requirements | 0.08 | 40 | 5 days |
| Assist in Data modeling / Design Logical Database | 0.04 | 20 | 5 days |
| Assist in define entities, attributes and relationships | 0.04 | 20 | 5 days |
| Make recommendations / suggestions on DBMS design | 0.014 | 7 | 1 day |
| Review Requirements | 0.04 | 20 | 5 days |
| Assist in HW / SW Planning | 0.04 | 20 | 5 days |
| Load RDBMS Software | 0.16 | 80 | 10 days |
| Install Database SW | 0.08 | 40 | 5 days |
| Manage DBMS Server Communication Parameters | 0.08 | 40 | 5 days |
| Create Database(s) and objects | 0.4 | 200 | 10 days |
| Create Physical DBMS | 0.08 | 40 | 5 days |
| Manage physical DBMS configuration | 0.08 | 40 | 5 days |
| Manage physical Database configuration | 0.08 | 40 | 5 days |
| Execute object DDL to create database objects | 0.08 | 40 | 5 days |
| Move database objects between physical structures | 0.08 | 40 | 5 days |
| Implement and test backup / recovery jobs / scripts |  |  |  |
| Assist in Define Database backup and recovery requirements and overall strategy | 0.068 | 34 | 5 days |
| Create and implement database backup solution | 0.04 | 20 | 5 days |
| Create and implement database recovery solution | 0.04 | 20 | 5 days |
| Implement & Deploy Processes and Tools | 0.24 | 120 | 20 days |
| Conversion of tools | 0.08 | 40 | 5 days |
| Install and maintain related DBMS management tools | 0.08 | 40 | 5 days |
| Load Data | 0.08 | 40 | 10 days |
| Complete DBA Security / Process Review Section | 0.24 | 120 | 15 days |

| Name | Estimated Work Effort Hours for 1 Server | Work Effort hours for 500 servers | Duration for 500 Servers |
| --- | --- | --- | --- |
| Assist in design database security userids / groups / roles | 0.08 | 40 | 5 days |
| Create / Initialize DBMS security roles | 0.08 | 40 | 5 days |
| Setup and maintain DBMS System Administration ID & privileges | 0.08 | 40 | 5 days |
| Update Documentation | 0.016 | 8 | 1 day |
| Maintain Operational Database Documentation | 0.016 | 8 | 1 day |
| Estimates total time for 1 Server Build ========================> | 10.658 |  |  |