## Sheet1
Project Phase | Totals | Consultant Days | Architect Days | Total Man Days
Solution Design |  | 3 | 7 | 10
Identify Key Solution and Staffing components
Design Single Sign-On Architecture
Design Login/Fail-over approach
Determine Application scripting approach and password change methods (if appropriate)
Scope Prototype Deployment Group
Develop a Project Plan with timeframes and milestones
Develop a Test Plan
Total Man days for Solution Design Phase: |  | 3 | 7 | 10
Develop SSO Solution in Lab
Install Single Sign-On on:
Primary & Backup SSO Servers |  |  | 1 | 1
Up to 4 development workstations |  | 1 |  | 1
Install SAFaccess on:
Primary & Backup Servers |  |  | 1 | 1
Up to 4 development workstations |  | 1 |  | 1
Create database objects, groups |  |  | 1 | 1
Develop Logon Scripts for Applications for: | # of? |  |  | 0
Basic Apps (Standard error checking) |  | 0 |  | 0
Normal Apps (Basic + password changes) |  | 0 |  | 0
Complex Apps (Normal w/ dual logins) |  | 0 |  | 0
Develop a Single Sign-Off script for SSO-enabled applications |  | 0 |  | 0
Verify SSO access software operation |  | 2 |  | 2
Test scripts for their reliability, availability, and performance |  | 2 |  | 2
Demonstrate developed solution to Customer Sponsor and Review Team |  | 0.5 |  | 0.5
Identify and document changes to the solution which must be made prior to prototype deployment |  | 0.5 |  | 0.5
Implement and Test final changes to developed solution |  | 2 | 1 | 3
Total Man days for Develop SSO Solution in Lab Phase: |  | 9 | 4 | 13
Deployment Prototype
Develop and document installation procedures for User workstations |  | 1.5 |  | 1.5
Develop and deliver training for personnel involved in the Prototype Deployment |  | 4 |  | 4
Build "Gold" image CD for standard User workstation installation |  | 1.5 |  | 1.5
Install Vendor (Solution) SSO on up to 20 additional User workstations |  | 2.5 |  | 2.5
Install SAFaccess on up to 20 additional User workstations |  | 2.5 |  | 2.5
Create additional database objects, groups |  | 1 |  | 1
Identify and document changes to the solution which must be made prior to production deployment |  | 2 |  | 2
Implement and Test changes to Final solution |  | 5 |  | 5
Total Man days for Deployment Prototype Phase: |  | 20 | 0 | 20
Total Days |  | 32 | 11 | 43